School Development Plan 2026-28

Attendance Action Plan 2026-27

| Operational leader | Lisa Sharpe Safeguarding Manager | SLT accountable lead | Emily Tobin Deputy Headteacher |
| --- | --- | --- | --- |
| SDP strand | Our Students | GB committee | Our Students |
| SDP Year 1 priority | Improve further attendance and engagement. | SDP strategy | Year 1 delivery of the SDP attendance/engagement goal through systematic monitoring, early family engagement and targeted intervention. |
| Governance purpose | Deliver the Year 1 milestones below and evidence impact, not activity alone. | Reporting | Termly SLT/committee scrutiny; FGB RAG three times yearly. |

Year 1 intended impact and success measures

| Intended impact • Robust attendance monitoring system embedded. • Fortnightly attendance scrutiny consistently implemented. • Families engage earlier with attendance concerns. • Attendance barriers identified and addressed promptly. • Increased use of targeted support and external services. • Improved student attendance and engagement. • Reduction in persistent absence rates. | Key success measures • Reduction in overall number of persistent absentees (below 90%). • Reduction in students at risk of becoming persistent absentees. • 100% fortnightly attendance reviews completed. • 100% weekly Safe and Well checks completed for non-attending students. • All attendance concerns managed in line with LA Attendance Protocols. • Increased parental engagement evidenced through meetings and communications. • Timely referrals made to LA statutory attendance team where thresholds are met. • Improved whole-school attendance compared to previous academic year. |
| --- | --- |

Year 1 termly delivery and RAG scrutiny

| Term | Priority deliverables | Evidence / success test | RAG | SLT / GB action |
| --- | --- | --- | --- | --- |
| 1 | • 1. Send AL1 letters to all students below 90% attendance or at risk of PA. • 2. Implement new attendance protocols using LA Operational Guide. • 3. Schedule fortnightly attendance scrutiny time. | • 1. Copies of AL1 letters sent • 2. Family contact logs • 3. Attendance tracking spreadsheet • 1. 100% of identified families receive an AL1 letter. • 2. Attendance reviewed fortnightly. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 2 | • 1. Continue fortnightly attendance monitoring. • 2. Identify and record barriers to attendance. • 3. Signpost families to appropriate support services. • 4. Discuss persistent attendance concerns at MDT meetings. | • 1. MDT Minutes • 2. Family Help and Support referrals • 3. Attendance intervention records • 4. Family Meeting records • 1. Barriers identified for all students below 90% | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 3 | • 1. Review impact of interventions implemented. • 2. Escalate concerns in line with attendance protocols. • 3. Undertake home visits where contact cannot be established. • 4. Complete weekly Safe and Well checks for non-attending students. | • 1. Safe and well check records • 2. Home visit logs • 3. Attendance review documentation • 4. Referral records • 100% of non-attending students receive weekly welfare checks. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 4 | • 1. Continue targeted support for persistent absentees. • 2. Strengthen partnership working with external agencies. • 3. Review attendance data and emerging patterns. • 4. Escalate unauthorised term time absences (mainly holidays) referrals to LA Attendance Team. | • 1. Agency Meeting notes • 2. Attendance analysis reports • 3. Referral confirmations • 4. Attendance plans • 1. Attendance interventions reviewed for all PAs | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 5 | • 1. Focus interventions on remaining students below 90%. • 2. Review effectiveness of attendance procedures. • 3. Share attendance expectations with families. • 4. Continue MDT discussions and safeguarding oversight. | • 1. Attendance Reports • 2. Family communication records • 3. MDT Minutes • 4. Case Reviews • 1. Increased attendance for targeted students. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 6 | • 1. Complete annual attendance review. • 2. Evaluate impact of new attendance protocols. • 3. Identify priorities for Year 2. • 4. Celebrate attendance improvements with students and families. | • Annual Attendance report. • Attendance comparison data . • Intervention evaluations. • Recognition records. • Success Measures. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |