School Development Plan 2026-28

Curriculum Development Action Plan – Primary Department

| Operational leader | Laura Cartwright Assistant Headteacher - Primary Department | SLT accountable lead | Emily Tobin Deputy Headteacher |
| --- | --- | --- | --- |
| SDP strand | Our Students | GB committee | Our Students |
| SDP Year 1 priority | Maintain excellence across ANC, BP and FP programmes. | SDP strategy | ANC: review curriculum and implement recommendations; BP: fully implement BeSST and strengthen PBS; FP: strengthen therapeutic and trauma-informed practice. |
| Governance purpose | Deliver the Year 1 milestones below and evidence impact, not activity alone. | Reporting | Termly SLT/committee scrutiny; FGB RAG three times yearly. |

Year 1 intended impact and success measures

| Intended impact Adapted National curriculum (ANC) • Curriculum improvements lead to improved student engagement, progress and outcomes in Reading, English and Maths, alongside increased engagement and progress across foundation subjects. • Enrichment opportunities are established and enhance the curriculum offer. Bespoke Provision (BP) • Consistent delivery of BeSST and strengthened PBS practice leads to improved student engagement, communication, regulation and readiness to learn. Flexible Provision (FP) • Every student has a clear vision and identifies next destinations, with targeted interventions supporting the skills needed to achieve their individual next steps. | Key success measures ANC • ANC curriculum review completed, with agreed recommendations implemented and monitored. • Evidence from assessment data shows progress in Reading, English and Maths, alongside identified improvements in foundation subject learning. • Enrichment opportunities are clearly mapped across all year groups with clear curriculum links. BP • BeSST is consistently delivered across BP, evidenced through planning, learning walks and curriculum monitoring. • Staff confidence and consistency in PBS approaches has increased. FP • All students have an identified next destination and personalised targets linked to the skills required to achieve it. • All students demonstrate measurable progress towards their identified next steps, evidenced through assessment and personalised learning outcomes. |
| --- | --- |

Year 1 termly delivery and RAG scrutiny

| Term | Priority deliverables | Evidence / success test | RAG | SLT / GB action |
| --- | --- | --- | --- | --- |
| 1 | • ANC – Complete learning walks and book scrutiny to establish the current position of curriculum implementation. • Bespoke Provision – Work alongside the Head of Therapies and PBS team to understand the implementation of the BeSST curriculum and identify three target classrooms to pilot the programme. • Flexible Provision – Observe current curriculum, staffing and intervention arrangements to establish the current position across the provision. | • Learning walks completed • Target classrooms identified and BeSST training completed with AHTs. • Observations in FP completed and intervention plans available for AHTs. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 2 | • ANC – Review findings from learning walks and book scrutiny and identify priority areas for curriculum development, including curriculum enrichment and assessment. • ANC – Complete an overview of the current reading offer across ANC and develop a Reading Action Plan to identify strengths, gaps and priorities for development. • Bespoke Provision – Work with the Head of Therapies and PBS team to develop the BeSST approach within the three identified pilot classrooms and establish how impact will be monitored. • Class teams involved in the pilot to be trained in delivering BeSST interventions. • Flexible Provision – Review observations and existing provision to identify priorities for intervention, curriculum delivery and student engagement, including consideration of students’ individual next steps and next destinations. | • ANC – Key strengths and priority areas for development identified and agreed. • ANC – Current reading offer mapped and Reading Action Plan completed, with clear priorities identified. • Bespoke Provision – BeSST approach agreed for the three pilot classrooms, with staff clear on expectations, implementation and monitoring arrangements established. • Flexible Provision – Key priorities identified, with agreed areas for development to support student engagement, individual next steps and next destinations. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 3 | • ANC – Begin implementing the agreed curriculum priorities identified through Term 1 and 2 monitoring. • ANC - Review curriculum enrichment experiences and opportunities, including off-site visits and meaningful encounters, to identify strengths and opportunities for development. • Bespoke Provision – Launch BeSST within the three identified pilot classrooms and monitor implementation alongside the Head of Therapies and PBS team. • Flexible Provision – Begin implementing agreed interventions and curriculum refinements linked to students’ individual next steps. | • ANC – Agreed curriculum priorities are being implemented consistently, with monitoring showing early improvements in identified areas. • ANC – Current enrichment offer reviewed, with strengths and areas for development identified. • Bespoke Provision – BeSST is being delivered within all three pilot classrooms, with staff receiving ongoing support and monitoring in place. • Flexible Provision – Agreed interventions and curriculum refinements are in place and linked to individual student next steps. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 4 | • ANC – Implement the Reading Action Plan and begin embedding agreed improvements across the ANC reading offer. • Begin implementing agreed developments to curriculum enrichment, including off-site visits and meaningful encounters • Bespoke Provision – Identify further classrooms for BeSST implementation and ensure relevant staff are trained and supported to deliver the intervention. • Flexible Provision – Develop the FP curriculum offer, including off-site provision and links with external providers, through the FP Coordinator. | • ANC – Reading Action Plan is being implemented, with agreed improvements embedded across the reading offer. • Enrichment developments are being implemented, with opportunities identified across ANC. • Bespoke Provision – Further classrooms identified for BeSST implementation and relevant staff trained to deliver the intervention. • Flexible Provision – Expanded and clearly defined FP curriculum offer in place, including identified off-site opportunities and links with external providers. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 5 | • ANC – Embed the Reading Action Plan and agreed improvements across the ANC reading offer. • Embed and further develop curriculum enrichment opportunities, including off-site visits and meaningful encounters. • Bespoke Provision – Embed BeSST implementation across the pilot and newly identified classrooms, ensuring staff are supported to deliver consistently. • Flexible Provision – Embed the developed FP curriculum offer, including off-site provision and links with external providers, through the FP Coordinator. | • ANC – Reading provision demonstrates consistent implementation of the Reading Action Plan. • A broader and more consistent range of meaningful enrichment experiences is being delivered across ANC. • Bespoke Provision – BeSST is being delivered consistently across identified classrooms, with relevant staff trained and supported. • Flexible Provision – The expanded FP curriculum offer is established and being delivered, including off-site and external provider opportunities. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 6 | • ANC – Evaluate the impact of the Reading Action Plan by comparing assessment data before and after implementation. • Evaluate the impact and range of curriculum enrichment opportunities, including off-site visits and meaningful encounters, and identify Year 2 priorities. • Bespoke Provision – Identify the final classrooms for BeSST implementation and identify staff training requirements to support future implementation. • Flexible Provision – Review RPI data and student progress across the provision to evaluate the impact of the curriculum and interventions and identify Year 2 priorities. | • ANC – Comparison of reading data demonstrates the impact of the Reading Action Plan on student progress, with Year 2 priorities identified. • Evaluation evidence demonstrates the impact of enrichment opportunities on student engagement and learning, with clear priorities for Year 2. • Bespoke Provision – Final classrooms identified, with training requirements established and a clear plan for implementation in Year 2. • Flexible Provision – RPI data and student progress evidence demonstrate the impact of the provision, with clear Year 2 priorities agreed. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |