School Development Plan 2026-28

Digital Citizenship Action Plan

| Operational leader | Laura Cartwright Assistant Headteacher - Primary Department | SLT accountable lead | Emily Tobin Deputy Headteacher |
| --- | --- | --- | --- |
| SDP strand | Our Students | GB committee | Our Students |
| SDP Year 1 priority | Maintain excellence across ANC, BP and FP; contributes to proactive safeguarding/online safety. | SDP strategy | Listed as an Our Students operational plan. Year 1 draft focuses on purposeful, inclusive use of technology; safeguarding interfaces should remain explicit. |
| Governance purpose | Deliver the Year 1 milestones below and evidence impact, not activity alone. | Reporting | Termly SLT/committee scrutiny; FGB RAG three times yearly. |

Year 1 intended impact and success measures

| Intended impact • A whole-school review of technology has been completed, identifying strengths, gaps and opportunities to enhance learning. • Staff confidence in using technology to support inclusion and engagement has increased. • Key recommendations have been implemented, improving access, participation and engagement. • Students are accessing a wider range of personalised, technology-supported learning approaches. | Key success measures • Whole-school technology review completed, with clear priorities and actions identified. • Staff survey and monitoring show increased confidence in using technology to support inclusion and engagement. • Agreed technology recommendations implemented across classrooms and learning environments. • Increased use of technology observed through learning walks, planning scrutiny and student voice. • Students demonstrate improved engagement and participation through technology-supported learning opportunities. |
| --- | --- |

Year 1 termly delivery and RAG scrutiny

| Term | Priority deliverables | Evidence / success test | RAG | SLT / GB action |
| --- | --- | --- | --- | --- |
| 1 | • Develop a shared understanding of Digital Citizenship and establish a clear whole-school definition that is understood and consistently applied by all staff. • To explore the current use of technology across ANC, Bespoke and Flexible Provision to identify strengths, gaps and opportunities for improvement. | • All staff demonstrate a shared understanding of Digital Citizenship and its application within school. • Technology use across ANC, Bespoke and Flexible Provision has been evaluated through learning walks, curriculum reviews and documentation scrutiny. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 2 | • Identify and prioritise up to three key areas where existing technology is underutilised to maximise its impact • Establish a cross-school technology working group, representing a range of roles and provisions, to support evaluation, development and implementation. | • Three key opportunities for improving the use of existing technology have been identified and prioritised. • A cross-school technology working group is in place. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 3 | • Oversee the technology working group to develop clear action plans, responsibilities and timescales for the three identified priority areas, ready for implementation. • Support the working group to identify and design whole-school training and professional development that will support staff to use technology effectively and purposefully across all provisions. | • Revised Clear action plans are in place for each of the three identified priority areas, with agreed actions, responsibilities and timescales. • A whole-school technology training plan has been developed, informed by the needs identified through the working group's evaluation and consultation. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 4 | • Oversee the technology working group in implementing the agreed actions across the three identified priority areas. • Explore a range of technology options that could support teaching, learning, communication, engagement and independence across the Primary and Secondary Departments, considering identified needs and available budget. | • The three identified priority areas are being implemented in line with agreed action plans, responsibilities and timescales. • A range of technology options has been researched and evaluated, with recommendations identified based on impact, suitability, accessibility and cost. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 5 | • Through the technology working group, evaluate the technology options explored and identify one Primary and one Secondary initiative for potential phased implementation through a two-year purchase and development plan. | • One Primary and one Secondary technology initiative have been identified and recommended by the working group. • A proposed two-year purchase and implementation plan has been developed, including anticipated costs, rationale, priorities and timescales, subject to available budget. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 6 | • Select one Primary and one Secondary classroom to pilot the identified technology initiatives and launch the pilot with clear aims and success criteria. • Evaluate the embedding and impact of technology across the whole school, including the increased and more purposeful use of existing technology. | • One Primary and one Secondary classroom are identified and actively piloting the new technology, with clear aims and success criteria in place. • Whole-school evaluation demonstrates how technology use has developed throughout the year, including evidence of increased and purposeful use of existing technology. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |