School Development Plan 2026-28

Digital Technology Development Action Plan 2026-27

| Operational leader | Mark Ashcroft IT and Data Manager | SLT accountable lead | Keri Myers School Business Manager |
| --- | --- | --- | --- |
| SDP strand | Our Resources | GB committee | Our Resources |
| SDP Year 1 priority | Create efficiencies in school administration through digitalisation and external specialist partnership. | SDP strategy | Improve efficiency of administrative functions through digitalisation. |
| Governance purpose | Deliver the Year 1 milestones below and evidence impact, not activity alone. | Reporting | Termly SLT/committee scrutiny; FGB RAG three times yearly. |

Year 1 intended impact and success measures

| Intended impact • Improved digital capability and operational efficiency through enhanced Arbor system integration, and attendance reporting. • A resilient, secure, and well-managed IT infrastructure that supports teaching, learning, and operational effectiveness while meeting or exceeding DfE Digital and Technology Standards. | Key success measures • Demonstrate compliance with a minimum of 75% of the DfE Digital and Technology Standards, measured through documented evidence of implementation. |
| --- | --- |

Year 1 termly delivery and RAG scrutiny

| Term | Priority deliverables | Evidence / success test | RAG | SLT / GB action |
| --- | --- | --- | --- | --- |
| 1 | • Deliver a resource booking application that enables all staff to allocate, reserve, and manage school resources efficiently. • Provide a secure guest Wi-Fi network for visitors, enabling appropriate internet access while maintaining the security and integrity of school systems and data. • Integrate the new phone system with Arbor to enable automatic caller recognition, allowing staff to instantly identify students when parents and guardians contact the school. | • Application available to all staff, enabling the booking of identified resources. • All guest’s being able to log on to the school Wi-Fi, with the necessary documentation. • Office staff are being presented with student’s details when receiving a call. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 2 | • Implement a centralised device management solution for all IT assets, ensuring the security, compliance, and effective management of devices and their data in line with DfE requirements. • Implement an IT Asset Management (ITAM) system that integrates with existing device management platforms to improve asset visibility, lifecycle management, and compliance with DfE requirements. • Develop integration between Arbor and the Business Intelligence (BI) platform to enable comprehensive Arbor reporting, including attendance monitoring and statutory reporting requirements. | • 100% of all IT devices are managed centrally. • 99% of all current IT assets are recorded and allocated to owners or locations. • Provide regular reporting on attendance. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 3 | • Review the school's local network infrastructure, including switching and UPS provision, against DfE Digital and Technology Standards. Develop an improvement plan with associated costs and recommendations to achieve compliance. • Review options for a resilient backup internet connection to support continuity of network services and meet DfE requirements for infrastructure resilience. | • Report delivered to SLT for review. • Proposal delivered for a backup solution, including costs and identify known risks. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 4 | • Develop a standardised SharePoint framework for School Business Management (SBM) functions to promote service consistency, collaboration, and centralised document management. • Review the current IT support model to identify opportunities for service improvement and implement an enhanced support solution that better meets the needs of staff and students. • Review annual technology expenditure against the approved budget and strategic priorities, and develop a forecasted budget for 2027 that aligns with technology requirements, DfE standards, infrastructure improvements, and planned digital initiatives. | • Provide SBM with SharePoint model proposals. • Implemented an improved IT support platform to enhance service delivery. • Produce a comprehensive technology roadmap for the following school year, outlining planned improvements, and expected outcomes. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 5 | • Review our disaster Recovery and Business Continuity Plan to ensure the continuity of critical school systems, data, and services in the event of a cyber incident, system failure, or other disruption. • Annual review of the school's filtering and monitoring arrangements to ensure compliance with DfE Digital and Technology Standards, safeguarding requirements. | • Complete and publish an updated Disaster Recovery and Business Continuity Plan. • Filtering systems are updated and maintained to effectively safeguard students and staff from inappropriate online content. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 6 | • Deliver planned Local Area Network (LAN) infrastructure improvements, including switching and network resilience enhancements, to meet DfE Digital and Technology Standards and support future digital requirement. • Conduct an annual review of staff and student devices, implementing a planned refresh and upgrade programme to ensure devices remain secure, reliable, and fit for purpose. | • A robust and centrally managed network is in place, providing greater reliability, improved security, simplified administration, and reduced downtime across the school. • All school devices are running supported operating systems and current security updates, improving cyber security, reliability, and the user experience while reducing organisational risk. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |