School Development Plan 2026-28

Examination Administration Action Plan

| Operational leader | Lexie McComasky Office Manager | SLT accountable lead | Keri Myers School Business Manager |
| --- | --- | --- | --- |
| SDP strand | Our Students | GB committee | Our Students |
| SDP Year 1 priority | Supports excellence in educational provision and accredited outcomes. | SDP strategy | Supporting operational plan: it is not separately named in the approved SDP list; its contribution is secure, compliant administration of accredited pathways. |
| Governance purpose | Deliver the Year 1 milestones below and evidence impact, not activity alone. | Reporting | Termly SLT/committee scrutiny; FGB RAG three times yearly. |

Year 1 intended impact and success measures

| Intended impact • A robust, compliant and efficient examinations process that ensures all registrations, entries, assessments and results are completed accurately and on time, with no breaches of regulations or missed opportunities for student accreditation. | Key success measures • 100% of student registrations and entries completed by awarding body deadlines. • 100% implementation of approved access arrangements. • Examination outcomes and certificates processed accurately and within required timescales. |
| --- | --- |

Year 1 termly delivery and RAG scrutiny

| Term | Priority deliverables | Evidence / success test | RAG | SLT / GB action |
| --- | --- | --- | --- | --- |
| 1 | • Publish annual examinations and assessment calendar. • Review previous examination series and identify improvements. • Audit all examination policies, procedures and contingency arrangements. | • Examination calendar issued to staff. • Annual exam review completed. • Policies updated and approved. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 2 | • Coordinate and administer November mock examinations. • Review mock outcomes with AHT-S. • Confirm registration requirements for the academic year | • Mock examinations completed as scheduled. • Feedback and actions agreed following mock review. • Registration and candidate information maintained accurately. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 3 | • Prepare examination entries and assessment schedules. • Complete compliance checks and examination readiness review. • Confirm staffing, rooming and access arrangement requirements. | • Entry tracking records maintained. • Compliance checks completed. • Examination arrangements communicated to relevant staff. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 4 | • Coordinate and administer March mock examinations. • Identify students requiring additional support. • Finalise arrangements for the May examination series. | • Mock examinations completed. • Actions identified from mock review. • May examination planning completed. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 5 | • Oversee the delivery of examinations, including access arrangements and invigilation. Coordinate examination materials and communication to awarding body, students and families. • Monitor examination processes and respond promptly to operational issues. • Complete post-examination administration in line with awarding body requirements. | • Examinations delivered in accordance with regulations. • Exam logs and records maintained. • Assessment materials returned within required timescales. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 6 | • Coordinate July resit opportunities where appropriate. • Process results, certification and student records. • Complete annual evaluation and identify priorities for improvement. | • Resit entries and assessments administered as required. • Results and certificates processed accurately. • End-of-year evaluation shared with Head of Centre. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |