School Development Plan 2026-28

Outdoor Learning Development Action Plan 2026-27

| Operational leader | Ryan Mason Assistant Headteacher - Secondary Department | SLT accountable lead | Emily Tobin Deputy Headteacher |
| --- | --- | --- | --- |
| SDP strand | Our Students | GB committee | Our Students |
| SDP Year 1 priority | Expand outdoor learning provision on and off site. | SDP strategy | Create and deploy the Outdoor Learning Coordinator role to expand opportunities. |
| Governance purpose | Deliver the Year 1 milestones below and evidence impact, not activity alone. | Reporting | Termly SLT/committee scrutiny; FGB RAG three times yearly. |

Year 1 intended impact and success measures

| Intended impact • 100% of students will access planned outdoor learning opportunities at least once per term, ensuring equitable access to learning beyond the classroom. • Student engagement during outdoor learning sessions will be sustained at 90% or above, as evidenced through lesson observations, engagement tracking and attendance records. • Student wellbeing measures will improve, with at least 75% of students reporting that outdoor learning positively supports their enjoyment of school, confidence and emotional wellbeing through student voice surveys. • Incidents of dysregulation during curriculum activities will reduce by at least 15% for identified students who regularly participate in outdoor learning provision. • All year groups will follow a progressive outdoor learning curriculum pathway, enabling students to develop increasingly complex practical, social and problem-solving skills over time. • Attendance for identified students with historically lower attendance will improve by at least 5%, supported through increased motivation, engagement and connection with school-based outdoor learning opportunities. • Staff confidence in delivering outdoor learning will increase, with 100% of teaching teams implementing planned outdoor learning experiences within their curriculum offer and reporting improved confidence through staff surveys. | Key success measures • 100% of students access at least one planned outdoor learning opportunity per term, evidenced through participation records. • Student engagement during outdoor learning sessions is sustained at 90% or above, evidenced through observations, engagement tracking and attendance data. • At least 75% of students report that outdoor learning positively impacts their confidence, wellbeing and enjoyment of school through student voice surveys. • Dysregulation incidents reduce by at least 15% for identified students who regularly participate in outdoor learning provision. • All year groups follow and demonstrate progress through a mapped outdoor learning curriculum pathway, developing increasingly complex practical, social and problem-solving skills. • Attendance for identified students improves by at least 5% from baseline levels, supported through regular participation in outdoor learning opportunities. • 100% of teaching teams deliver planned outdoor learning experiences within their curriculum offer and report increased confidence through staff surveys. |
| --- | --- |

Year 1 termly delivery and RAG scrutiny

| Term | Priority deliverables | Evidence / success test | RAG | SLT / GB action |
| --- | --- | --- | --- | --- |
| 1 | • 1. Increase visibility of Outdoor Learning Co-ordinator to staff and families. • 2. Develop and communicate a whole school vision for outdoor learning • 3. Complete an audit of current outdoor learning provision across the school. | • OLC to lead on whole school initiatives that increase their visibility to all staff. • OLC to write newsletter article to share her role with families and some upcoming initiatives • OLC to work with Commando Joes to create a clear progression of outdoor learning experiences from EYFS to Post-16. • OLC to create delivery plan for RESPECT programme to pilot with FP. • Audit all current outdoor learning provisions to include current offer to students and resources required based on environment. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 2 | • 1. OLC to work with AHTS to embed Outdoor Learning Across the Curriculum. • 2. Identify barriers to participation and accessibility and create a delivery plan to ensure engagement for all students. • 3. OLC to deliver CPD to class-based staff with suggested activities. | • Clear progression of outdoor learning activities to support class-based staff to use the environment to enhance learning. • Provide staff with a bank of activities that they can lead with students during play and lunch time and other curriculum or enrichment activities. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 3 | • 1. OLC to gather staff and student voice regarding outdoor learning opportunities. • 2. OLC to visit other settings to gain ideas to further enhance OL offer. • 3. OLC to link with external providers to enrich our outdoor learning offer and provide students with offsite opportunities. | • OLC to create and distribute student surveys to capture student voice around outdoor learning offer. • OLC to link up with other settings and external providers to moderate and quality assure our offer against what else is provided locally and adapt ALS offer where appropriate. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 4 | • 1. OLC to support staff to link outdoor learning to EHCP target progression. • 2. OLC to assess student engagement and enjoyment within sessions and link to school experience. • 3. Link up with Careers Advisor/Transitions Co-ordinator to support student aspirations and pathways linked to outdoor learning. | • OLC to meet with class teams and support where EHCP targets for students can be met within outdoor learning provision. • Share with CA and TC names of students who have shown a keen interest or skills set related to outdoor activity. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 5 | • 1. Develop outdoor learning spaces across the school. • 2. Create spaces that support wellbeing and encourage personal development. • 3. Support with further embedding of outdoor learning initiatives across school such as horticulture, orienteering, climbing etc. | • OLC to create ideas and a plan of how to develop outdoor spaces and share with AHTs and SBM/FM. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 6 | • 1. OLC to work with AHTs to review the outdoor learning offer, highlighting successful aspects and suggesting changes ahead of next academic year. • 2. Lead on outdoor learning day ensuring it is an opportunity to celebrate the use of outdoors to enhance learning opportunities. • 3. Complete a final audit of provision across school, including spaces, resources, curriculum activities to ensure a clear and robust delivery plan is created ahead of next academic year. | • OLC to co-ordinate outdoor learning day and support with other whole school initiatives, working with key staff to create an outstanding offer for students. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |