School Development Plan 2026-28

Restrictive Physical Intervention (RPI) Reduction Action Plan

| Operational leader | Claire Welch Head of Therapies | SLT accountable lead | Emily Tobin Deputy Headteacher |
| --- | --- | --- | --- |
| SDP strand | Our Students | GB committee | Our Students |
| SDP Year 1 priority | Increase physical safety of students and staff and reduce the need for RPI. | SDP strategy | BP: fully implement BeSST and strengthen PBS expertise; FP: strengthen therapeutic and trauma-informed practice. |
| Governance purpose | Deliver the Year 1 milestones below and evidence impact, not activity alone. | Reporting | Termly SLT/committee scrutiny; FGB RAG three times yearly. |

Year 1 intended impact and success measures

| Intended impact • To improve the quality of support across the school, and to reduce restrictive intervention incidents. | Key success measures • Reduction in restraint incidents by 30%. • Reduction in repeat restraint incidents involving identified students. • 100% of classrooms audited through SaLT, OT and PBS processes. • 100% of classroom One-Page Profiles reviewed and embedded. • Increased staff confidence in supporting communication, regulation and behaviour by at least 20%. • Increased consistency across classrooms as evidenced through audit outcomes and learning walks. • Improved student engagement and readiness to learn. • Reduction in crisis presentations requiring Flexible Provision. |
| --- | --- |

Year 1 termly delivery and RAG scrutiny

| Term | Priority deliverables | Evidence / success test | RAG | SLT / GB action |
| --- | --- | --- | --- | --- |
| 1 | • Baseline SaLT, OT and PBS classroom audits; review communication/sensory/proactive support. • Train leaders in PBS problem-solving; analyse restraint patterns and identify high-risk cohorts. • Train PBS team in BeSST and establish Early Years/Year 1 pilots. | • Completed audit reports. • Behaviour and restraint data. • Staff confidence survey. • Leadership training records. • BESST | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 2 | • Implement audit recommendations and update One-Page Profiles. • Begin leadership learning walks; review Flexible Provision staffing. • Model BeSST in pilots and establish engagement/readiness-to-learn measures. | • Updated One-Page Profiles. • Learning walk records. • Audit action plans. • Flexible Provision review. • 80% of audit recommendations implemented. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 3 | • Coach teams after incidents; sample fidelity of One-Page Profiles and target MDT/AHT support. • Analyse restraint themes and review Flexible Provision interventions. • Extend BeSST phase and train pilot staff. | • Incident analysis. • Classroom planning scrutiny. • Meeting records. • BESST observation records. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 4 | • Secure effective Flexible Provision capacity and review reintegration. • Re-audit priority classrooms and provide targeted SaLT/OT/PBS coaching. • Evaluate BeSST pilots and continue incident monitoring. | • Flexible Provision outcome data/report. • Re-audit reports. • Incident data. • BESST evaluation report. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 5 | • Train second-phase BeSST classrooms and embed practice in pilots. • Share effective practice and target support at higher-restraint classes. • Complete whole-school confidence/fidelity checks and learning walks. | • Case studies. • Learning walk reports. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 6 | • Evaluate annual restraint data, SaLT/OT/PBS audits, Flexible Provision and BeSST. • Use staff, student and parent feedback to evidence impact. • Set Year 2 priorities from restraint, confidence, consistency, reintegration and learning-readiness evidence. | • Annual restraint report. • Audit summaries. • Staff confidence survey. • Parent and student feedback. • Governors | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |