School Development Plan 2026-28

Safeguarding Development Action Plan 2026-27

| Operational leader | Lisa Sharpe Safeguarding Manager | SLT accountable lead | Emily Tobin Deputy Headteacher and Designated Safeguarding Lead |
| --- | --- | --- | --- |
| SDP strand | Our Students | GB committee | Our Students |
| SDP Year 1 priority | Increase proactive safeguarding support, including online safety; ensure every student’s feeling of belonging and inclusion. | SDP strategy | Enhance proactive safeguarding by using increased Safeguarding Team capacity. |
| Governance purpose | Deliver the Year 1 milestones below and evidence impact, not activity alone. | Reporting | Termly SLT/committee scrutiny; FGB RAG three times yearly. |

Year 1 intended impact and success measures

| Intended impact • Proactive Safeguarding and Online Safety • Increased visibility and effectiveness of the safeguarding team. • Earlier identification and intervention for safeguarding concerns. • Improved student understanding of online risks and safe online behaviour. • Increased confidence in reporting concerns. • Enhanced parental awareness of online safety risks. • Reduced repeat online safety incidents. | Key success measures • All students receive online safety education during the year. • Reduction in repeat online safety incidents recorded on CPOMS. • Increase in early help and preventative safeguarding interventions. • Students demonstrate increased awareness of safeguarding reporting routes. • Increase in students reporting that they feel safe in school. • Increase in students reporting a sense of belonging and inclusion. • Improved attendance and engagement of identified vulnerable students. • Positive feedback from students, families and staff regarding safeguarding support. |
| --- | --- |

Year 1 termly delivery and RAG scrutiny

| Term | Priority deliverables | Evidence / success test | RAG | SLT / GB action |
| --- | --- | --- | --- | --- |
| 1 | • 1. Identify key online safety themes and concerns from CPOMS records • 2. Raise awareness with families regarding online risks • 3. Introduce student safeguarding forums to gather feedback on online safety concerns and emerging risks. • 4. Establish baseline student voice regarding belonging and inclusion • 5. Identify vulnerable students | • 1. CPOMS analysis. • 2. Student forum minutes • 3. Parent communications • 4. Safeguarding team meeting minutes • 5. Student surveys | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 2 | • 1. Deliver targeted online safety sessions to students • 2. Develop an online safety resource bank for families • 3. Increase early intervention for students presenting safeguarding concerns • 4. Increase opportunities for student voice • 5. Introduce targeted support for identified students | • 1. Student sessions • 2. Family resources shared • 3. CPOMS records • 5. Student feedback • 6. Student voice records | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 3 | • 1. Analyse safeguarding and online safety trends • 2. Deliver workshops for vulnerable student groups • 3. Increase safeguarding visibility across school. • 4. Promote reporting routes for students • 5. Monitor student wellbeing and sense of belonging | • 1. Trend analysis reports • 2. Student surveys • 3. Workshop attendance records • 4. Safeguarding displays and resources • 5. Wellbeing surveys | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 4 | • 1. Review impact of online safety interventions • 2. Work with families where online concerns are recurring • 3. Deliver safeguarding updates to staff • 4. Strengthen multi-agency working • 5. Deliver activities to promote diversity and inclusion | • 1. Intervention reviews • 2. Family meeting records • 3. Staff training records • 4. Agency meeting notes • 5. Event records | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 5 | • 1. Target support for students with ongoing safeguarding concerns • 2. Deliver preventative online safety campaigns. • 3. Share good practice across school • 4. Further support students reporting low levels of belonging • 5. Promote transition support where required | • 1. CPOMS Audits • 2. Case Studies • 3. Team reports • 4. Campaign Materials • 5. Student voice surveys | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 6 | • 1.Complete safeguarding review • 2. Evaluate the use of the additional safeguarding capacity • 3. Identify priorities for year 2 • 4. Celebrate positive safeguarding outcomes • 5. Complete annual review of belonging and inclusion | • 1. Annual Safeguarding Report • 2. Student voice outcomes • 3. Safeguarding data analysis • 4. Survey comparisons • 5. Celebration events | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |