School Development Plan 2026-28

School Sufficiency Action Plan 2026-27

| Operational leader | Keri Myers School Business Manager | SLT accountable lead | Ania Hildrey Headteacher |
| --- | --- | --- | --- |
| SDP strand | Our Resources | GB committee | Our Resources |
| SDP Year 1 priority | Increase capacity on existing and potentially additional sites to meet demand for places. | SDP strategy | With Liverpool City Council, explore on-site and off-site capacity growth. |
| Governance purpose | Deliver the Year 1 milestones below and evidence impact, not activity alone. | Reporting | Termly SLT/committee scrutiny; FGB RAG three times yearly. |

Year 1 intended impact and success measures

| Intended impact • The school successfully implements its short-term sufficiency plan through the installation and occupation of temporary accommodation by January 2027, creating additional pupil capacity and reducing immediate operational pressures. • A clear medium-term strategy is agreed with Liverpool City Council regarding the development of an Abbot’s Lea School@ satellite provision, including agreement on accommodation requirements and exploration of suitable sites. | Key success measures • Temporary accommodation operational by January 2027. • Additional pupil places created. • Staffing structure expanded to support growth. • Educational outcomes maintained despite increasing demand. • No adverse impact on safeguarding, wellbeing or quality of provision. • Medium -Term Success Measures • Abbot’s Lea School@ model agreed in principle. • Feasibility work completed. |
| --- | --- |

Year 1 termly delivery and RAG scrutiny

| Term | Priority deliverables | Evidence / success test | RAG | SLT / GB action |
| --- | --- | --- | --- | --- |
| 1 | • 1. Finalise plans for temporary accommodation expansion • 2. Analyse future demand projections and pupil place requirements • 3. Continue strategic discussions with Liverpool City Council regarding sufficiency planning | • Temporary accommodation project approved. • Local Authority meeting records. • Demand forecasting report. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 2 | • 1. Install and commission additional temporary accommodation. • 2. Secure approvals and commence implementation of temporary accommodation project. • 3. Review staffing requirements associated with additional pupil numbers. | • Temporary accommodation project underway. • Workforce impact assessment completed. • Project milestones agreed. • Initial satellite provision options identified. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 3 | • 1. Increase available pupil capacity. • 2. Complete operational readiness review. • 3. Ensure staffing, safeguarding and ICT arrangements are in place | • Temporary accommodation operational by January 2027. • Additional pupil places created. • Staff recruited and deployed where required. • Safeguarding and compliance checks completed. • Educational provision maintained without disruption | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 4 | • 1. Evaluate effectiveness of temporary expansion. • 2. Develop detailed specification for any future satellite site • 3. Continue engagement with Liverpool City Council regarding future opportunities • 4. Undertake formal options appraisal for the Abbot’s Lea School@ model. • 5. Consider the relocation of either EYFS or Sixth Form provision. | • Evaluation report completed. • Preferred satellite model identified. • Site specification document completed. • Agreement in principle on next steps with Local Authority. • Capacity pressures mitigated through temporary provision. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 5 | • 1. Explore potential sites capable of accommodating an Abbot’s Lea School@ provision. • 2. Assess sites against agreed criteria. • 3. Review workforce and operational implications of a multi-site model. | • Potential sites identified. • Feasibility studies completed. • Site assessment reports completed. • Workforce planning review completed. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 6 | • 1. Present recommendations on preferred Abbot’s Lea School@ option. • 2. Agree next phase of implementation with Liverpool City Council. • 3. Establish strategic direction for long-term new school solution. | • Preferred satellite option identified. • Local Authority agreement secured regarding future direction. • Long-term capacity strategy developed. • Governors approve Year 2 priorities. | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |