Operational Action Plan

School Development Plan 2026-28 | Year 1 delivery: 2026-27

Transitions Development Plan

| Operational leader | Emily Tobin Deputy Headteacher | SLT accountable lead | Ania Hildrey Headteacher |
| --- | --- | --- | --- |
| SDP strand | Our Students | GB committee | Our Students |
| SDP Year 1 priority | Maintain excellence across ANC, BP and FP programmes. | SDP strategy | Enhance transitions through the new Transitions Coordinator role. |
| Governance purpose | Deliver the Year 1 milestones below and evidence impact, not activity alone. | Reporting | Termly SLT/committee scrutiny; FGB RAG three times yearly. |

Year 1 intended impact and success measures

| Intended impact • Increased capacity to manage tribunal process • Increased aspirations about next destinations (whether within or beyond school) • Clear process mapping of all transition points • Increased support for families navigating transition points • Increased uptake of transitions by students deemed ready • Increased uptake of the Supported Internship Programme | Key success measures • Clear process maps will exist for all transition points by September 2027 • Family-friendly transition packs to be created for sharing with families at key junctions, commencing in Term 5 2026 • At least 50% of those deemed ready by AHTs to move to next destinations in the summer term 2026 • To have at least 4 employers offering Supported Internships for September 2027-28 |
| --- | --- |

Year 1 termly delivery and RAG scrutiny

| Term | Priority deliverables | Evidence / success test | RAG | SLT / GB action |
| --- | --- | --- | --- | --- |
| 1 | • To fully induct the new Transitions Coordinator (TC) on admission to ALS, life within ALS and exit from ALS • To observe transition events, including but not limited to Open Evening | • Induction schedule • Starter interview • TC feedback | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 2 | • For TC to fully understand and support the tribunal process | • Information provided to SLT on a regular basis | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 3 | • For TC to gain an understanding of the diverse post-16 pathways available to our students and to understand the EHCP review process for Year 11+ | • Process map created • TC feedback and task completion | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 4 | • To secure Supported Internship offers from at least 3 employers for September 2027 | • Formal agreements made | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 5 | • For TC to shadow the process for creating the September 2027 set-up and to capture this in a process map | • Process map created | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |
| 6 | • To evaluate the progress made in 2026-27 with the above actions and to set clear targets for 2027-28, including the TC leading processes as opposed to shadowing and learning | • PM cycle complete and targets set. • Knowledge audit completed | ☐ R ☐ A ☐ G | Progress / barrier: Corrective action / decision: |